## Sheet1
Nine Mile Community Center Renovations
Sep 2012 - Nov 2013
| Materials | 10% Contractor Fee | Labor
Item #1 - Repairs to External Walls |  |  | 1600
Lumber - Fir incl soffits to match | 2721.11 | 272.111
Miscellaneous materials (nails, etc)
Item #2 - Paint Building Exterior | 1157.47 | 115.747 | 6770
6/20/13 | 342.07 | 34.207
Item #3 - New door downstairs closet
Doors - Home Resource | 140 | 14
Installation charge (Sanding/Refinishing) |  |  | 800
Item #4 - New Entrance Door |  |  | 400
Cost of New Door | 1750 | 188.077
Door Knob/Lock | 130.77 | 13.077
Lumber for exterior trim incl in #1
Item #5 - Replace floor covering entryway |  |  | 610
Abbey Carpet | 1368 | 136.8
Item #6 - Electrical work
Light fixtures - interior (Western Mt Lighting) | 1069.5 | 161.96 | 500
Light fixtures - exterior | 550.1 | 55.01
Item #7 - Repair Church exterior
Item #8- Install mirrors | 119.98 | 11.998 | 50
Item #9 - Inspect roofing (Labor in item #5)
Item #10 - Walls around furnace |  | 109.81 | 1550
Drywall materials - Boyce Lumber | 343.7
Wainscoting - Buckeye Hardwood | 754.4
Item #11 - Remediate wood stove
Anderson Masonry | 2162 | 216.2 | 200
Item #12 - Electrical permit at cost (submitted to Bay) | 57 | 5.7
Change Order #1 - Removal of Fuel Tank | 200 | 20 | 400
Change Order #2 - Palmer Electric Basement Wiring | 261.11 | 26.111 | 200
Change Order #3 - Third Mirror | 59.99 | 5.999 | 25
Change Order #4 - Furnace Room, Trim, Moulding | 1450.94 | 145.094 | 450
Change Order #5 - Glazing Exterior Windows 6/20/13 | 487.29 | 48.729 | 575
Change Order #6 - Elec code upgrade bldg rear | 315.1 | 31.51 | 240
Totals | 15440.53 | 1612.14 | 14370 | 31422.67
Resources
Restricted Gift December 2011 - Guthrie | 3000
Historical Museum Grant | 2800
Preserve Historic Missoula Paint Grant | 500
Donated Lighting Fixtures | 1619.6
Donated Mirrors | 119.98
Donated Door Knob/Lock | 130.77
Albans Donation | 100
Robinson Donation | 90.989
Restricted Gift August 2012 | 15000
Restricted Gift October 2012 - Guthrie | 2000
Restricted Gift January 2013 - MacDowell | 1000
Restricted Gift May 2013 | 2000
Restricted Gift June 2013 | 2574.73
Restricted Gift November 2013 | 486.6
31422.669